Skilled Multiplatforms

Implementation Plan — Priority Roadmap

April 2026  •  Based on Initial Codebase Audit

# Executive Summary

A comprehensive audit of the Skilled Multiplatforms codebase has revealed that while the project has a solid architectural vision — a .NET MAUI mobile client backed by an ASP.NET Core API and a shared EF Core data layer — the vast majority of the implementation is either missing, hardcoded with placeholders, or broken. The app cannot currently launch, connect to a database, or perform any real user-facing operation.

This document outlines the three phases of work required to bring the product to a functional, testable state: standing up the core API and database, wiring the mobile client to real data, and completing the UI and testing layers.

# Current Status Snapshot

| Area | Component | Completion | Severity |
| --- | --- | --- | --- |
| API | Controllers & Endpoints | 0% | 🔴 Critical |
| API | Authentication / JWT | 0% | 🔴 Critical |
| Database | PostgreSQL running | No | 🔴 Critical |
| Database | Migrations applied | No | 🔴 Critical |
| Configuration | API URL (hardcoded placeholder) | No | 🔴 Critical |
| Configuration | Secrets management | No | 🔴 Critical |
| Models | ServiceProvider fields | 40% | 🟠 High |
| Models | Entity relationships | 50% | 🟠 High |
| Services | Service implementations | 20% | 🟠 High |
| ViewModels | Integration with services | 10% | 🟠 High |
| XAML / Views | Property binding correctness | 40% | 🟠 High |
| Navigation | Shell routing | 50% | 🟠 High |
| UI Pages | Core pages completed | 30% | 🟠 High |
| Testing | Unit tests | None | 🟡 Medium |
| Testing | Integration tests | None | 🟡 Medium |
| Build / Deploy | CI/CD & environment configs | None | 🟡 Medium |

# Phase 1 — Critical Foundation  (Week 1)

Nothing in the application can function until the API exists and the database is running. Phase 1 must be completed in full before any testing or UI work makes sense. Every task here is a blocker for everything else.

## 1.1  Stand Up the PostgreSQL Database

The app depends on a PostgreSQL instance running on localhost:5433 with a database named skilled_db. Currently neither exists and the database initializer is never called at startup.

Step 1 — Run Postgres:  Install and start PostgreSQL 15+ (or run via Docker:

docker run -d -p 5433:5432 -e POSTGRES_PASSWORD=<secret> postgres:15

Step 2 — Run migrations:  Apply all pending EF Core migrations from Skilled.Data to create the schema.

Step 3 — Call DatabaseInitializer:  Wire DatabaseInitializer.InitializeAsync() into MauiProgram.cs inside a DI scope immediately after app.Build() so the schema is created on first run.

Step 4 — Secure the connection string:  Move the database password out of appsettings.json and into User Secrets (already configured) or environment variables. Never commit credentials.

## 1.2  Build the Core API Controllers

The API project currently contains only the template WeatherForecast endpoint. The following controllers are the minimum required for the app to function at all. Each should follow RESTful conventions and return standard JSON responses.

| Controller | Key Endpoints | Depends On |
| --- | --- | --- |
| AuthController | POST /auth/register, POST /auth/login, POST /auth/refresh, POST /auth/logout | 1.1 (DB) |
| UsersController | GET /users/me, GET /users/{id}, PUT /users/{id} | AuthController |
| ProvidersController | GET /providers, GET /providers/{id}, GET /providers/{id}/services | 1.1 (DB) |
| ServicesController | GET /services, GET /services/{id}, GET /services/category/{id} | 1.1 (DB) |
| BookingsController | POST /bookings, GET /bookings, GET /bookings/{id}, PATCH /bookings/{id}/status | Auth + Services |
| ReviewsController | POST /reviews, GET /reviews/provider/{id} | Bookings |
| MessagesController | GET /chats, GET /chats/{id}/messages, POST /chats/{id}/messages | Auth + Users |
| PaymentsController | POST /payments, GET /payments/{id} | Bookings |

## 1.3  Implement JWT Authentication Middleware

AuthService.cs exists but is non-functional. GetCurrentUserAsync() calls itself recursively, RefreshTokenAsync() is inaccessible, and no actual token validation is wired into the API pipeline.

Add JWT middleware:  Add Microsoft.AspNetCore.Authentication.JwtBearer to the API project.

Configure signing key:  Configure the JWT signing key in User Secrets (not appsettings.json).

Protect endpoints:  Apply [Authorize] to all controllers except /auth/register and /auth/login.

Fix AuthService:  Rewrite AuthService.GetCurrentUserAsync() to read the token from secure storage and call the API, removing the recursive call.

Token refresh:  Implement token refresh logic so sessions survive past the initial token expiry.

## 1.4  Fix Configuration and Secrets Management

All three projects have hardcoded placeholder URLs and exposed credentials. This must be resolved before any real deployment or team testing.

API URL:  Replace all instances of https://skilled-api.yourdomain.com/api with a config-driven value read from appsettings.json, user secrets, or an environment variable.

Dev config:  Create appsettings.Development.json for the API with local dev values.

MAUI secrets:  Load user secrets in MauiProgram.cs for local development.

Documentation:  Add an .env.example file documenting all required environment variables.

# Phase 2 — Data Layer and Mobile Integration  (Week 2)

With the API running and the database connected, Phase 2 focuses on making the MAUI mobile client actually talk to real data. This means fixing broken models, completing service implementations, and replacing all mock data in ViewModels.

## 2.1  Complete the Data Models

Several models are missing fields that the XAML views already try to bind, causing runtime crashes. The following additions are required before any UI work can proceed.

| Model | Missing Properties | Impact |
| --- | --- | --- |
| ServiceProvider | UserId (FK), BusinessName, AverageRating, TotalReviews, YearsOfExperience, IsVerified, ProfileImageUrl | Crashes HomePage.xaml bindings |
| User | CreatedAt, UpdatedAt, IsVerified, Bio, PhoneNumber | Incomplete user profiles |
| ChatPreview | HasUnreadMessages (computed from UnreadCount) | Crashes MessagesPage.xaml |
| Review | CreatedAt, UpdatedAt | Missing audit fields |
| Payment | BookingId (FK), RefundAmount, RefundStatus | Cannot link payments to bookings |

## 2.2  Configure Entity Relationships in DbContext

The EF Core context (SkilledDbContext.cs) is missing navigation properties and relationship configurations. Without these, ORM queries will not load related data correctly.

User ↔ ServiceProvider:  Define the one-to-one relationship between User and ServiceProvider via UserId.

ServiceProvider ↔ TradeService:  Configure ServiceProvider → TradeService one-to-many with cascade delete.

Pricing types:  Register ServicePricing and CostRange as owned types or separate entities in OnModelCreating (they are currently defined but not mapped).

Location / service area:  Add ServiceProvider → Location relationship for service area coverage.

New migration:  Create and run a new migration after all model changes are applied.

## 2.3  Fix Service Implementations

All three service classes (AuthService, UserService, TradeServiceService) have critical bugs that prevent them from working even if the API were running.

AuthService — recursive call:  Remove the recursive call to GetCurrentUserAsync() inside itself. Replace with the correct token-reading and API-calling logic.

TradeServiceService — URL params:  Fix GetServicesByCategoryAsync() — it currently passes the full TradeCategory object as a URL parameter. Change to pass category.Id (an integer).

UserService — URL params:  Fix UserService.GetServiceProvidersByCategoryAsync() with the same URL parameter issue.

DI lifetime:  Change all service DI registrations in MauiProgram.cs from Singleton to Scoped to prevent shared state and memory leaks.

Error handling:  Add consistent error handling across all services — currently exceptions are swallowed and null is returned silently.

## 2.4  Replace Mock Data in ViewModels

Every ViewModel currently populates its lists with hardcoded mock objects instead of calling the injected services. This must be replaced across all ViewModels for the app to show real data.

HomeViewModel:  Call TradeServiceService.GetServicesByCategoryAsync() to populate the services list. Remove all hardcoded TradeService objects.

BookingsViewModel:  Call BookingService to load real bookings for the logged-in user. Wire up the filter tabs (All / Upcoming / Completed / Cancelled) to query the API accordingly.

MessagesViewModel:  Call MessagesService (to be created) to load real chat threads. Remove hardcoded ChatPreview objects.

RegisterViewModel:  Replace the stub registration alert with a real call to AuthService.RegisterAsync(), including confirmation password validation.

LoginPageViewModel — navigation:  Fix the post-login navigation from //MainTabs/HomePage to the correct registered Shell route (to be fixed in 2.5).

## 2.5  Fix Navigation and Shell Routing

The Shell routing is 50% configured. LoginPageViewModel navigates to //MainTabs/HomePage which is not a registered route, causing an immediate crash on successful login.

Audit all routes:  Audit AppShell.xaml and AppShell.xaml.cs and list all routes that are referenced in GoToAsync() calls throughout the app.

Register missing routes:  Register every page used in navigation (ServiceDetailPage, BookingPage, etc.) in AppShell.xaml.cs using Routing.RegisterRoute().

Verify TabBar:  Confirm the TabBar structure in AppShell.xaml matches the routes being navigated to.

End-to-end navigation test:  Test each navigation path manually (login → home → service detail → booking → confirmation).

# Phase 3 — UI Completion and Testing  (Week 3)

With a working API and wired-up mobile client, Phase 3 focuses on completing the placeholder UI pages and establishing a test baseline so the team can confidently iterate without regressions.

## 3.1  Complete Placeholder Pages

The following pages currently contain only a title label or a literal "This is a placeholder" string. Each needs full UI implementation.

ServiceDetailPage:  Provider photo, name, rating, reviews, service list with pricing, "Book Now" CTA, map/location section.

BookingsPage:  Filterable list of bookings (Upcoming / Completed / Cancelled). Each row shows provider, service, date, status badge.

ProfilePage:  User avatar, name, email, phone. Edit profile form. Provider verification badge if applicable.

ServiceListPage:  Filterable/searchable list of services in a chosen category. Card layout matching the design pattern from HomePage.

BookingPage:  Date/time picker, service selection, notes field, price summary, "Confirm Booking" button.

SettingsPage:  Notification preferences, account management, logout, app version.

## 3.2  Write Unit Tests

Skilled.Tests currently contains a single empty test class (UnitTest1.cs). The following test coverage is the minimum needed to develop with confidence.

AuthService tests:  AuthService: Register, Login, token refresh, invalid credentials, expired token.

UserService tests:  UserService: GetCurrentUser, GetServiceProviders, filter by category.

TradeServiceService tests:  TradeServiceService: GetByCategory, GetById, filter and sort.

HomeViewModel tests:  HomeViewModel: LoadServices populates list, handles API errors gracefully.

BookingsViewModel tests:  BookingsViewModel: Filter logic correctly segments upcoming/completed/cancelled.

Fix test project references:  Add project references in Skilled.Tests.csproj to Skilled.Services and Skilled.Data.

## 3.3  Write Integration and API Tests

Unit tests alone are insufficient for a marketplace app with authentication and database interactions. The following integration tests will catch issues that unit tests miss.

API test harness:  Use WebApplicationFactory to spin up the API in memory for each test.

Auth integration test:  Auth flow: Register → Login → access protected endpoint → refresh token → logout.

Booking integration test:  Booking flow: Create service → create booking → update status → fetch booking.

Test database:  Use a test PostgreSQL instance (or SQLite in-memory) seeded with fixture data.

## 3.4  Build and Deployment Infrastructure

To allow the team to test on real devices and eventually ship, the following infrastructure work is needed.

Dockerise the API:  Create a Dockerfile for Skilled.API (multi-stage build: SDK → runtime).

docker-compose:  Add a docker-compose.yml that starts both the API and a PostgreSQL container with one command for local developer onboarding.

Production config:  Create appsettings.Production.json with production-safe defaults (no secrets).

CI pipeline:  Add a GitHub Actions (or equivalent) workflow that builds, tests, and lints on every PR.

Seed data:  Add a database seed script with sample providers, services, and bookings so testers have data to work with immediately.

# Consolidated Priority Order

The table below lists every task in the recommended execution order. Nothing in a later row should be started until the rows it depends on are complete.

| # | Task | Phase | Effort | Blocks |
| --- | --- | --- | --- | --- |
| 1 | Run PostgreSQL & create skilled_db | Phase 1 | 2h | Tasks 2–5 |
| 2 | Apply EF Core migrations | Phase 1 | 1h | Tasks 3–5 |
| 3 | Wire DatabaseInitializer in MauiProgram.cs | Phase 1 | 30m | Task 5 |
| 4 | Move secrets to User Secrets / env vars | Phase 1 | 1h | All teams |
| 5 | Build AuthController (register + login) | Phase 1 | 1d | Tasks 6–12 |
| 6 | Implement JWT middleware in API | Phase 1 | 4h | All API |
| 7 | Build UsersController | Phase 1 | 4h | Task 11 |
| 8 | Build ProvidersController + ServicesController | Phase 1 | 1d | Tasks 9–12 |
| 9 | Build BookingsController | Phase 1 | 1d | Tasks 10, 13 |
| 10 | Build ReviewsController + PaymentsController | Phase 1 | 1d | Task 13 |
| 11 | Build MessagesController | Phase 1 | 1d | Task 16 |
| 12 | Replace hardcoded API URL with config value | Phase 1 | 1h | All MAUI |
| 13 | Add missing properties to data models | Phase 2 | 4h | Tasks 14–17 |
| 14 | Configure entity relationships in DbContext | Phase 2 | 4h | Task 15 |
| 15 | Create and run new EF migration | Phase 2 | 1h | Phase 2 data |
| 16 | Fix AuthService (remove recursion) | Phase 2 | 2h | Task 17 |
| 17 | Fix URL params in UserService & TradeServiceSvc | Phase 2 | 1h | Task 18 |
| 18 | Replace all ViewModel mock data with real calls | Phase 2 | 2d | Tasks 19–20 |
| 19 | Fix Shell routing & navigation crashes | Phase 2 | 4h | Task 20 |
| 20 | Fix XAML binding mismatches | Phase 2 | 4h | Task 21 |
| 21 | Complete ServiceDetailPage UI | Phase 3 | 1d | — |
| 22 | Complete BookingsPage UI | Phase 3 | 1d | — |
| 23 | Complete ProfilePage, BookingPage, SettingsPage | Phase 3 | 2d | — |
| 24 | Write unit tests for all services + ViewModels | Phase 3 | 2d | — |
| 25 | Write API integration tests | Phase 3 | 2d | — |
| 26 | Dockerise API + docker-compose for local dev | Phase 3 | 1d | Deployment |
| 27 | Add CI/CD pipeline (build + test on PR) | Phase 3 | 1d | Deployment |
| 28 | Add seed data for testers | Phase 3 | 4h | — |

# Key Principles for the Implementation

Never start Phase 2 tasks in parallel with Phase 1.  The API and database must exist before any MAUI service call can succeed. Working on the mobile client before the API is running is wasted effort.

Fix the models before fixing the views.  Every XAML binding crash is caused by a missing model property. Add the properties first, then the bindings will resolve correctly.

Replace mock data immediately after wiring a service.  Leaving mock data in a ViewModel while implementing the real service call creates confusion about whether the UI is showing real or fake data.

Write the test for each service at the same time as you fix it.  Writing tests after the fact is slower and covers less ground. Adding a test alongside each bug fix ensures regression coverage from day one.

Use the docker-compose environment for all team testing.  Developers should not need to manually configure PostgreSQL. A single docker-compose up should produce a fully running local environment.

This plan was generated from a full codebase audit conducted April 2026.  Priority order is based on inter-task dependencies, not estimated effort.